## Cover Page
TEAM NAME
W Team
Prepared By:
LIST TEAM MEMBER FULL NAMES
Huu Tin Pham
Deep Patel
Guyass Rozybakiev
Khaled Oulhaci
Jacob Atallah
Jingyu Zeng

## Product backlog
Issue # | User Story Title/Task Title | Task Description | Story Points (1,2,3,4,5) | Due Date | Priority | Risk | Assignmed Members
#1 | Story 1: As a new user, I want to create an account, so that I can save my recipes and meal plans. | Design registration form (email, password, confirm password) Client-side validation (required fields, password rules) Backend API endpoint for user registration Hash and store passwords securely Handle duplicate email errors Return success/error responses Redirect user after successful registration | 5 | 2026-02-06 | High | Medium | Jacob, Khaled, Guyass, Tin, Deep, Jingyu
#2 | Story 2: As a registered user, I want to log in, so that I can access my saved data. | Design login form Client-side validation Backend login endpoint Password verification Implement session or token-based authentication Store auth token securely (cookie/local storage) Handle invalid credentials Redirect to dashboard or meal planner | 3 | 2026-02-06 | High | Medium | Jacob, Khaled, Guyass, Tin, Deep, Jingyu
#3 | Story 3: As a user, I want to manage my profile information, so that the app can personalize recipes and meal plans. | Create profile page UI Fields for diet preferences (e.g. vegetarian, vegan) Fields for allergies (multi-select or text input) Backend endpoint to fetch profile data Backend endpoint to update profile data Save preferences to database Validate inputs Show confirmation on save | 3 | 2026-02-06 | Medium | Low | Jacob, Khaled, Guyass, Tin, Deep, Jingyu
#4 | Story 4: As a user, I want to create a recipe, so that I can reuse it in my meal plans. | Design recipe creation form Fields: Title, Ingredients list, Preparation steps, Prep time, Difficulty, Cost estimate, Dietary tags Client-side validation. Backend API to create recipe Associate recipe with user Save recipe to database Show success message | 5 | 2026-02-27 | High | Medium | Jacob, Khaled, Guyass, Tin, Deep, Jingyu
#5 | Story 5: As a user, I want to edit my recipes, so that I can keep them up to date. | Fetch recipe data by ID Pre-fill form with existing data Allow editing of all fields Backend API to update recipe Validate ownership (user can only edit their recipes) Save updated recipe Show confirmation feedback | 3 | 2026-02-27 | Medium | Low | Jacob, Khaled, Guyass, Tin, Deep, Jingyu
#6 | Story 6: As a user, I want to delete a recipe, so that I can remove recipes I no longer use. | Add delete action (button/icon) Confirmation modal Backend API to delete recipe Validate ownership Remove recipe from database Handle cases where recipe is used in meal plans Refresh recipe list after deletion | 2 | 2026-02-27 | Medium | Medium | Jacob, Khaled, Guyass, Tin, Deep, Jingyu
#7 | Story 7: As a user, I want to search recipes by name or ingredients, so that I can quickly find what I need. | Add search input field Implement debounce for search input Backend search endpoint Query recipes by title and ingredients Return matching results Display search results list Handle empty state (no results) | 5 | 2026-02-27 | Medium | Medium | Jacob, Khaled, Guyass, Tin, Deep, Jingyu
#8 | Story 8: As a user, I want to filter recipes, so that I can find meals that match my needs. | Design filter UI: Time, Difficulty, Cost, Dietary tags Backend filtering logic Combine filters with search Update results dynamically Reset/clear filters option | 5 | 2026-02-27 | Medium | Medium | Jacob, Khaled, Guyass, Tin, Deep, Jingyu
#9 | Story 9: As a user, I want to create a weekly meal plan, so that I can organize my meals in advance. | Add delete action (button/icon) Confirmation modal Backend API to delete recipe Validate ownership Remove recipe from database Handle cases where recipe is used in meal plans Refresh recipe list after deletion | 5 | 2026-03-27 | Medium | Medium | Jacob, Khaled, Guyass, Tin, Deep, Jingyu
#10 | Story 10: As a user, I want to view my meals in a weekly grid, so that I can easily see my plan. | Design weekly grid UI (days × meal types) Fetch meal plan data for selected week Map meals to grid cells Handle empty cells Allow switching between weeks Loading and error states | 5 | 2026-03-27 | High | High | Jacob, Khaled, Guyass, Tin, Deep, Jingyu
#11 | Story 11: As a user, I want to assign a recipe to a specific day and meal type, so that my plan is structured. | Add “Add meal” interaction in grid Recipe selection modal/dropdown Backend API to assign recipe to slot Validate: No duplicate recipe in the same week, Valid day and meal type Save assignment Update UI immediately | 3 | 2026-03-27 | Medium | Medium | Jacob, Khaled, Guyass, Tin, Deep, Jingyu
#12 | Story 12: As a user, I want to edit or remove meals from my planner, so that I can adjust my week. | Add edit/remove options to each meal slot Confirmation before removal Backend API to update or delete meal assignment Update planner UI Handle edge cases (missing recipe, deleted recipe) | 5 | 2026-03-27 | High | High | Jacob, Khaled, Guyass, Tin, Deep, Jingyu
#13 | Story 13: As a user, I want the planner to prevent duplicate recipes in the same week, so that my meals stay varied. | Track assigned recipes per week Backend validation for duplicates Frontend warning message Disable already-used recipes in selector Handle error responses gracefully | 5 | 2026-03-27 | High | High | Jacob, Khaled, Guyass, Tin, Deep, Jingyu
|  | Total | 54

## Time blog
Sprint 1: | Tin | Guyass | Khaled | Jacob | Deep | Jinyu
Login page | 0 | 0 | 60 | 60 | 0 | 0
Registration page | 0 | 0 | 60 | 60 | 0 | 0
Home page | 0 | 0 | 30 | 30 | 0 | 0
Landing page | 0 | 0 | 15 | 15 | 0 | 0
Meal preferences | 0 | 120 | 0 | 0 | 0 | 0
Environment Configuration | 0 | 15 | 15 | 15 | 0 | 0
Database Configuration | 0 | 60 | 60 | 60 | 0 | 0
Sprint Planning | 120 | 0 | 0 | 0 | 120 | 60
User stories | 60 | 0 | 0 | 0 | 60 | 60
Meetings | 120 | 120 | 120 | 120 | 120 | 120
Total (minutes): | 300 | 315 | 360 | 360 | 300 | 240
Total hours | 31.25